## READ ME
This quarterly status update form is used to provide required quarterly updates for CMAQ/CRP, CRRSAA, STP, and TAP-L funded
projects.
When completing this form:
1. Start with the prior quarter's form, or with the form submitted with your funding application. If this is your first time completing the form, start with a blank form.
2. Refer to the Quarterly Status Update Instructions on the funding program website.
If completing this form for the first time during a call for projects:
1. If you haven't already, start your eTIP application to receive a TIP ID
2. Note the TIP ID and Project Title used in your eTIP application in the <enter project name> and <enter TIP ID> fields on the Update form
3. Follow the Instructions for Initial submittals only section of the Quarterly Status Update Instructions
If updating this form during a call for projects (because the project has been awarded some funding in the past or has been included on a contingency list):
1. If you haven't already, start your eTIP application to receive a TIP ID
2. Note the TIP ID and Project Title used in the current eTIP application cycle - and any assigned in prior cycles - in the <enter project name> and <enter TIP ID>
fields on the Update form
3. Refer to the Quarterly Status Update Instructions on the funding program website.
TIP! If you're working on laptop or small screen, on the Update form you can select View > Freeze Panes > Unfreeze Panes to allow a larger number of input
rows to be visible on your screen.

## Update form
Quarterly Status Update Form for CMAQ/CRP, CRRSAA, STP, and TAP-L projects processed through IDOT/FHWA
Project: | <enter project name> |  |  |  | TIP ID: | <enter TIP ID> |  |  | For CMAP/Council use only:
CMAQ CRRSSA-SF STP-SF
TAP-L CRRSAA-L STP-L
UPDATE INFORMATION |  |  |  |  | PROJECT INFORMATION |  |  |  | Active Contingency Deferred
Application
| Completed By: | Date:
Initial Submittal |  |  |  |  | Environmental Class of Action: |  | <class of action> |  | <status> |  | <date> | 2023-01-12 | Today's date
Most Recent Prior Update |  |  |  |  | Target Construction Letting: |  | <date> | Enter the current target date (m/d/yy)
Current Update |  |  |  |  | Current construction cost estimate: |  | <whole dollars> | Enter the current estimate, excluding CE
Final "Actual" Dates |  |  |  |  | Change in estimate since prior update: |  | <whole dollars> | Enter 0 if no change, or enter amount of change (+ or -)
[5 empty] | Most recent PPI approval: |  | <date> | If no PPI approved, do not enter a date
MILESTONE INFORMATION
| No changes from prior update | If any cells below are highlighted, changes must be made - please uncheck the "No changes" box and address the highlighted items | [9 empty] | FALSE | No changed
| Milestone (Shaded lines required for federally-funded phases only) | Initial Estimated Date (m/yyyy) | Complete? | Updated Estimated Date (m/yyyy) | Actual Date (m/d/yyyy) | Attachments (R - Required, O - Optional) | Sponsor/Implementer Comments (will be shaded if notes are added) |  |  | Notes/Instructions
Pre-phase 1 | Project Scoping |  | <yes/no>
| Application for ENG1 Funds |  | <yes/no or n/a>
| Phase 1 QBS Advertisement |  | <yes/no or n/a>
| Phase 1 QBS Closed |  | <yes/no or n/a>
| Consultant Selected by Local Council/Board |  | <yes/no or n/a> |  |  | Meeting minutes (O)
Phase 1 ENG | Engineering Agreement submitted (BLR 5530) |  | <yes/no or n/a>
Federally-funded | LAA submitted (BLR 5310PE) |  | <yes/no or n/a> | [8 empty] | FALSE | E1 fed
| Engineering Agreement Approved (BLR 5530) |  | <yes/no or n/a> |  |  | Notice to proceed (O) |  |  |  | expected 8-12 months after draft submittal
| LAA approved (BLR 5310PE) |  | <yes/no or n/a> |  |  | Approved agreement (R) |  |  |  | expected 8-12 months after draft submittal
| Phase 1 Kick-off Held |  | <yes/no> |  |  | Meeting minutes (R)
| Initial PPI Submittal |  | <yes/no or n/a>
| Initial PPI Approval |  | <yes/no or n/a> |  |  | PPI Form (R) |  |  |  | expected 5-10 days after draft submittal
| 1st State/Fed Coord Meeting |  | <yes/no or n/a> |  |  | Meeting minutes (R)
| Environmental Action Concurrence |  | <yes/no or n/a> |  |  | Copy of email/letter/form (R)
| Environmental Survey Request (ESR) submitted |  | <yes/no or n/a> |  |  | Copy of request (O) |  |  |  | See BLRS manual for environmental requirements
| Cultural |  | <yes/no or n/a>
| Section 4(f) approval |  | <yes/no or n/a> |  |  | Copy of approval form/letter (O) |  |  |  | If "n/a" selected, attach form BLR 22410
| Section 6(f) approval |  | <yes/no or n/a> |  |  | Copy of approval form/letter (O)
| Historic Preservation Compliance |  | <yes/no or n/a> |  |  | Copy of approval form/letter (O)
| Noise |  | <yes/no or n/a>
| Floodplain |  | <yes/no or n/a>
| Wetland |  | <yes/no or n/a>
| Wetland Impact Evaluation (WIE) |  | <yes/no or n/a>
| Bio - USFWS Coordination |  | <yes/no or n/a>
| EcoCAT submitted |  | <yes/no or n/a>
| Special Waste |  | <yes/no or n/a>
| PESA Requested |  | <yes/no or n/a> |  |  | Copy of request
| PESA Completed |  | <yes/no or n/a>
| PSI Requested |  | <yes/no or n/a> |  |  | Copy of request
| PSI Completed |  | <yes/no or n/a>
| Public Meeting |  | <yes/no or n/a>
| Subsequent State/Fed Coord Meeting |  | <yes/no or n/a>
| Subsequent State/Fed Coord Meeting |  | <yes/no or n/a>
| Subsequent State/Fed Coord Meeting |  | <yes/no or n/a>
| Project Dev. Report (BLR 19100, 22210, or 22211) Submitted |  | <yes/no or n/a> |  |  | Copy of transmittal/cover only (R)
| Project Dev. Report (BLR 19100, 22210 or 22211) Approved |  | <yes/no or n/a> |  |  | Signature page (R)
| Phase 1 Design Approval Received |  | <yes/no> |  |  | Signature page (R)
| Initial Invoice (BLR 5620, 5621) |  | <yes/no or n/a>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no>
Phase 2 ENG | Application for ENG2 Funds |  | <yes/no or n/a>
Federally-funded | Phase 2 QBS Advertisement |  | <yes/no or n/a> | [8 empty] | FALSE | E2 fed
| Phase 2 QBS Closed |  | <yes/no or n/a>
| Consultant Selected by Council/Board |  | <yes/no or n/a> |  |  | Meeting minutes (O)
| Updated PPI Submittal |  | <yes/no or n/a>
| Updated PPI Approval |  | <yes/no or n/a> | [6 empty] | expected 5-10 days after draft submittal
| Engineering Agreement submitted (BLR 5530) |  | <yes/no or n/a>
| LAA submitted (BLR 5310PE) |  | <yes/no or n/a>
| Engineering Agreement Approved (BLR 5530) |  | <yes/no or n/a> |  |  | Notice to proceed (O) |  |  |  | expected 8-12 months after draft submittal
| LAA approved (BLR 5310PE) |  | <yes/no or n/a> |  |  | Approved agreement (R) |  |  |  | expected 8-12 months after draft submittal
| Phase 2 Kick-off Held |  | <yes/no or n/a> |  |  | Meeting minutes (R)
| State/Fed Coord Meeting |  | <yes/no or n/a> |  |  | Meeting minutes (R)
| Pre-final plans submitted |  | <yes/no> |  |  | Copy of transmittal only (R) |  |  |  | Do not attach a full set of plans
| Comments received |  | <yes/no> | [6 empty] | expected 1-4 months after draft submittal
| Final Plans, Specs, and Estimates submitted |  | <yes/no> |  |  | Copy of transmittal (R) |  |  |  | Do not attach a full set of plans
| Initial Invoice (BLR 5620, 5621) |  | <yes/no>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no>
ROW | Application for ROW funds |  | <yes/no or n/a>
None required | Updated PPI Submittal |  | <yes/no or n/a> | [8 empty] | FALSE | ROW none
Federally-funded | Updated PPI Approval |  | <yes/no or n/a> |  |  | Approved PPI (R) |  |  |  | expected 5-10 days after draft submittal |  | FALSE | ROW fed
| LAA submitted (BLR 5310PE) |  | <yes/no or n/a> | [6 empty] | expected 4-6 months after draft submittal
| LAA approved (BLR 5310PE) |  | <yes/no or n/a> |  |  | Approved Agreement (R) |  |  |  | expected 4-6 months after draft submittal
| Initiated |  | <yes/no>
| Completed |  | <yes/no>
| Certified |  | <yes/no>
| Initial Invoice (BLR 5620, 5621) |  | <yes/no>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no>
Construction/CE | Application for CON/CE funds |  | <yes/no or n/a>
CON federally-funded | Updated PPI Submittal |  | <yes/no or n/a> | [8 empty] | FALSE | CON fed
CE federally-funded | Updated PPI Approval |  | <yes/no or n/a> |  |  | Approved PPI (R) |  |  |  | expected 5-10 days after draft submittal |  | FALSE | CE fed
| Draft Construction Agreement submitted (BLR 5310C) |  | <yes/no or n/a>
| Draft Construction Eng Agreement submitted (BLR 5530) |  | <yes/no or n/a>
| Final Construction Agreement submitted (BLR 5310C) |  | <yes/no or n/a> | [6 empty] | expected 4-6 months after draft submittal
| Final Construction Eng Agreement submitted (BLR 5530) |  | <yes/no or n/a> | [6 empty] | expected 4-6 months after draft submittal
| Final Construction Agreement approved (BLR 5310C) |  | <yes/no or n/a> |  |  | Approved Agreement (R) |  |  |  | expected 3-4 months after draft submittal
| Final Construction Eng Agreement approved (BLR 5530) |  | <yes/no or n/a> |  |  | Approved Agreement (R) |  |  |  | expected 3-4 months after draft submittal
| Letting |  | <yes/no>
| Bid Acceptance |  | <yes/no>
| Notice to Proceed |  | <yes/no>
| Initial Invoice (BLR 5620, 5621) |  | <yes/no>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no>
Other project activities | Project groundbreaking ceremony |  | <yes/no or n/a>
| Project ribbon cutting ceremony |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>

## drop-down values
Dropdown: CA (cell H4) | Dropdown: CAStat (cell H4) | Dropdown: LetType (cell H5) | General
<class of action> | <status> | <type> | <yes/no or n/a> | <yes/no>
CE, Group 1, No report (State Approval) | Anticipated | State | Yes | Yes
CE, Group 1, with report (State Approval) | Approved | Local | No | No
CE, Group 2 (Federal Approval) |  |  | N/A
Environmental Assessment (EA)
Env. Impact Statement (EIS)