## Update form
Quarterly Status Update Form for CMAQ/CRP, CRRSAA, STP, and TAP-L projects processed through FTA
Project: |  |  |  |  | TIP ID: |  |  |  | For CMAP/Council use only:
CMAQ CRRSSA-SF STP-SF CRP
UPDATE INFORMATION |  |  |  |  | PROJECT INFORMATION |  |  |  | TAP-L CRRSAA-L STP-L
Active Contingency Deferred App
| Completed By: | Date:
Initial Submittal |  | <mm/dd/yyyy> |  |  | Environmental Class of Action: |  | <class of action> |  | <status> |  | <approval date>
Most Recent Prior Update |  | <mm/dd/yyyy> |  |  | Environmental Approval: |  | <environmental approval type>
Current Update |  | <mm/dd/yyyy> |  |  | Current construction/implementation cost estimate: |  | <whole dollars>
Final "Actual" Dates |  | <mm/dd/yyyy> |  |  | Change in estimate since prior update: |  | <whole dollars> | <describe primary reason(s) for change>
MILESTONE INFORMATION
No changes from prior update
Phase Groups | Milestone (Shaded lines required for federally-funded phases only) | Initial Estimated Date (m/yyyy) | Complete? | Updated Estimated Date (m/yyyy) | Actual Date (m/d/yyyy) | Attachments (R - Required, O - Optional) | Sponsor/Implementer Comments |  |  | FTA Project and Construction Management Guidelines section reference
Project Development/ Pre-engineering | Systems Planning |  | <yes/no> | [6 empty] | 2.2.1
| Alternatives Analysis |  | <yes/no or n/a> | [6 empty] | 2.2.2
| Project Management Plan (PMP) |  | <yes/no or n/a> | [6 empty] | 2.2.3
| Environmental Assessment/Mitigation Plan |  | <yes/no or n/a>
| Design Control Plan |  | <yes/no or n/a>
| Real Estate Acquisition and Management Plan (RAMP) |  | <yes/no or n/a> | [6 empty] | 4.5.1
| Safety and Security Management Plan (SSMP) |  | <yes/no or n/a> | [6 empty] | 2.2.11
| Project Delivery and Procurement Plan |  | <yes/no or n/a> | [6 empty] | 2.2.6
| Environmental Planning |  | <yes/no or n/a> | [6 empty] | 2.2.7
| Section 4(f) evaluation |  | <yes/no or n/a> | [6 empty] | 2.2.7.3
| Section 106 (Historic Preservation) process |  | <yes/no or n/a> | [6 empty] | 2.2.7.4
| NEPA process initiated |  | <yes/no or n/a>
| NEPA process completed (ROD, FONSI, or CE determination) |  | <yes/no or n/a> | [6 empty] | 4.4
| Preliminary Design Drawings |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Preliminary Specifications and Design Standards |  | <yes/no or n/a>
| Preliminary Contract Packaging Plan |  | <yes/no or n/a>
| Preliminary Cost Estimates |  | <yes/no or n/a>
| Preliminary Contract Documents |  | <yes/no or n/a>
| Preliminary right-of-way plans |  | <yes/no or n/a>
| Preliminary utility plans |  | <yes/no or n/a>
| Preliminary third-party agreements and permits |  | <yes/no or n/a>
Engineering and Design | FTA grant application in TrAMS |  | <yes/no or n/a> |  |  | Copy of application (O) | <Enter temporary grant # here>
Federally-funded | FHWA to FTA transfer request to IDOT |  | <yes/no or n/a> |  |  | Copy of request letter (R)
| FTA grant approval |  | <yes/no or n/a> |  |  |  | <Enter FTA grant # here>
| Consulant selection |  | <yes/no or n/a>
| Final Design Drawings |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Specifications and Design Standards |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Contract Packaging Plan |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Cost Estimates |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Contract Documents |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final right-of-way plans |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final utility plans |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final third-party agreements and permits |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final construction bid packages |  | <yes/no or n/a> | [6 empty] | 2.3.4
| Final construction management plan |  | <yes/no or n/a> | [6 empty] | 2.3.4
| Initital design review |  | <yes/no or n/a> | [6 empty] | 4.7.3.1
| Final verification |  | <yes/no or n/a> | [6 empty] | 4.7.3.2
ROW | FTA grant application in TrAMS |  | <yes/no or n/a> |  |  | Copy of application (O) | <Enter temporary grant # here>
None required | FHWA to FTA transfer request to IDOT |  | <yes/no or n/a> |  |  | Copy of request letter (R)
Federally-funded | FTA grant approval |  | <yes/no or n/a> |  |  |  | <Enter FTA grant # here>
| Consulant selection |  | <yes/no or n/a>
| Initiation |  | <yes/no or n/a>
| Negotiations |  | <yes/no or n/a>
| Completion |  | <yes/no or n/a>
Construction | FTA grant application in TrAMS |  | <yes/no or n/a> |  |  | Copy of application (O) | <Enter temporary grant # here>
CON federally-funded | FHWA to FTA transfer request to IDOT |  | <yes/no or n/a> |  |  | Copy of request letter (R)
| FTA grant approval |  | <yes/no or n/a> |  |  |  | <Enter FTA grant # here>
| Contractor selection |  | <yes/no or n/a>
| Notice to proceed |  | <yes/no or n/a>
| Constuction started |  | <yes/no or n/a>
| Construction completed |  | <yes/no or n/a>
| FTA grant closed |  | <yes/no or n/a>
Other project activities | Funding announcement/press release |  | <yes/no or n/a>
| Ground-breaking event |  | <yes/no or n/a>
| Ribbon-cutting event |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>

## drop-down values
Dropdown: CA (cell H4) | Dropdown: CAStat (cell H4) | Dropdown: LetType (cell H5) | General |  | Dropdown: EnvApproval (cell H7)
<class of action> | <status> | <type> | <yes/no or n/a> | <yes/no> | <environmental approval type>
Class 1: Env. Impact Statement (EIS) | Anticipated | State | Yes | Yes | FONSI
Class 2: Categorical Exclusion (CE) | Approved | Local | No | No | ROD
Class 3: Environmental Assessment (EA) |  |  | N/A